## Slide 1
ХVIII Meeting of the
Monitoring Committee of
Operational programme “Transport” 2007-2013
.
2 – 3 June 2015
Pravets

## Slide 2
Chart: Financial implementation of OPT by 20.05.2015 г. (euro)
| Budget | Grant awarded | Value of eligible expenditure of commercial contracts (eligible) | Paid | EU Funding | Certified to the EC (EU share) | Paid by EC after certification (EU share)
 | 2003.4812 | 2014.2011 | 1963.5757 | 1494.1135 | 1624.4796 | 1127.3631 | 1107.7119
 | 1.0054 | 0.9801 | 0.7458 | 0.69398 | 0.68189

## Slide 3
Chart: Financial implementation of OPT by priority axis by 20.05.2015 г. (euro)
| ПО 1 | ПО 2 | ПО 3 | ПО 4 | ПО 5
Budget | 660000000 | 909587365 | 333193801 | 34750000 | 65950000
Paid | 516013128.61 | 630166865.32 | 292898985.28 | 23481413.29 | 31553115.13
Certified to the EC | 388519994 | 460526384 | 238170327 | 15867420 | 24278964

## Slide 4
Achieved results
  In the period since the previous session completed the following projects:
  Extension of the Metropolitan Sofia Stage III, Lot 1 "Tsarigradsko Shose” “Sofia Airport”, Lot 2 "Mladost 1 - Business Park Mladost 4 ". As a result, completed and put into operation 21 stations and 21.6 km of new metro lines
Lot 2 of the project for "Maritza„ MW (the official opening of the project took place on May 28, 2015)
In January 2015 started a project to build an Integrated system for traffic management
Coastal centers of Varna and Burgas part of the project VTMIS - signed Act №15
  In the period since the previous session:
Physical implementation of the project "Reconstruction and electrification of the railway Plovdiv-Svilengrad” increased from 55% to 70%
Physical implementation of the project "Modernization of the railway Septemvri - Plovdiv ” increased from 22% to 45%
ХVIII Meeting of OP “Transport” 2007-2013 Monitoring Committee

## Slide 5
Measures to complete the implementation of OPT 2007-2013
Necessary to be invested the remaining resource of 500 million euros by the end of 2015
In order to achieve it:
  Full mobilization of contractors and beneficiaries of OPT
  Enhancing coordination, monitoring and control of "high-risky" projects
  Support the implementation of the railway projects by the EIB
  Provide financial resources to complete projects
  Realistic assessment of the status and projections for the completion of projects and preparation of an Action plan
ХVIII Meeting of OP “Transport” 2007-2013 Monitoring Committee

## Slide 6
Action Plan for 2015
OP “Transport” 2007–2013 (1)
Finalization of the procedure for approval of the Project for construction of the Gabrovo Bypass The Bulgarian Government confirmed its engagement for construction of the Shipka Tunnel (20 May 2015)
2. Phasing of OPT Major Projects
A. Lot 2 of the “Western Arc of the Sofia Ring Road” Project
B. “Plovdiv-Burgas” Railway Project (reduction of the scope with a value of 20 million EUR - three sub-stations, design and build of signaling of Burgas Railway junction)
Necessary actions: Modification of the Decisions of the EC for approval of major projects and re-programming of OPTTI 2014-2020 - end of July
3. Secure budget for the Projects not finished within the eligibility period (by the end of 2015)
Necessary for completion of the projects during 2016 - EUR 130 million (90 million EUR for rail and 40 million EUR for road projects)
4. Decision on increasing the percentage of the Cohesion Fund co-financing up to 85% and reduction of the national co-financing in the formation of Grants to 85%/15%
ERDF – not foreseen
Cohesion Fund – 77 million EUR (32 million EUR of railway projects и 45 million EUR of road projects)
ХVIII Meeting of OP “Transport” 2007-2013 Monitoring Committee

## Slide 7
Action Plan for 2015
OP “Transport” 2007–2013 (2)
The Proposal has been discussed and approved by the Council of Ministers with Protocol № 18/07.05.2015
Necessary actions: Modification of the OPT and the decisions of the EC for approval of the major projects (railway and road), co-financed under the CF - end of July
5. Identification of Projects with opportunities for “Reverse Phasing” (earlier start of projects from the programming period 2014 - 2020)
Extension of the second metro line between “James Boucher” Metro Station and “Hladilnika” District, Metro Station Vitosha(OPTTI Project)
Necessary Actions:
• Amendment of the OPT Financing Plan (transfer of funds from PA 5 to PA 3 within ERDF) - end of July
• Approval of a non-major project under OPT and a non-major project under OPTTI
The proposal for amendment/modification of OPT 2007 – 2013 is foreseen to cover all the amendments up to end - middle of July 2015.
6. Using the opportunities foreseen in the provisions of Art. 77, paragraph 2 of Regulation 1083/2006 for 10 % „Flexibility“.
ХVIII Meeting of OP “Transport” 2007-2013 Monitoring Committee

## Slide 8
Decisions closing OPT 2007-2013
  1. OPT MC took note of the action plan for completion of the OPT
  2. OPT MC has no objection to the proposed amendment to the financial plan of the program by increasing the contribution of CF to 85% respectively reduction of national co-financing to 15%
  3. OPT MC agrees MA OPT to take action to possibly phasing the following projects: West arc of Sofia Ring Road - Lot 2 (PA2); Modernization of the railway line Plovdiv-Burgas (PA1); Modernization of the railway line in Septemvri - Plovdiv (PA1)
  4. OPT MC agrees MA OPT to take action to change the budgets of the different priorities by transferring funds between them within the relevant Fund
ХVIII Meeting of OP “Transport” 2007-2013 Monitoring Committee

## Slide 9: Annual Report Implementation of OPT for 2014
Drafted in accordance with Regulations 1083/2006 and 1828/2006
Contents information by the end of 2014 about:
  Overall physical and financial implementation
  Monitoring and evaluation measures
  Physical and financial implementation of investment projects
  Information and publicity measures
  Significant problems:
  Land acquisition procedures
  Archaeological research
  Unfavorable climatic conditions
  Delay coordination between institutions involved in the consistency procedures during the preparation and implementation of projects financed under OPT
  Accumulation of delay from the original deadlines for completion

## Slide 10
Thank you for your attention!
www.optransport.bg