## Slide 1: SOFIA METRO EXTENSION PROJECT INCLUDED IN THE OPTTI 2014-2020 г.
MS Vitosha – commissioned on 20.07.2016

## Slide 2
S C H E M E
of location of Sofia Metro sections included in the OPTTI 2014-2020 – Stage 1 and 2 of Line 3 and the extension of Line 2 “MS J. Bourchier – MS Vitosha”

## Slide 3: 1. Extension of Line 2: Section “MS J. Bourchier (MS ІІ-11) – MS Vitosha (MS ІІ-12)” and equipment for changing the traffic direction after MS “Vitosha” /2014-2016/
- Length – 1.3 km - underground
- Number of stations - 1 underground
- Scope of construction - 950 m underground according to NATM
metro station and underpass facilities – cut-and-cover method in a reinforced ditch and the adjacent engineering infrastructure.
- Achieved tender price – EUR 21.6 mln. /EUR 17 mln/km/
Phase 1 – under OPT 2007-2013; Phase 2 – under OPTTI 2014-2020.
- Construction duration - 22 months starting on 08. 2014.
Completed - 06.2016. Put into operation – 07.2016
- Contractors: Tunnel – Stanilov Ltd.; Metro station – G.P. Group Ltd.
- Beneficiary - SM – Metropoliten JSC

## Slide 4
Technology phases of the construction of the
Tunnel under Cherni Vrah blvd. under NATM
- Execution of excavation works of the
calotte and the structure of the arch
- Execution of the works related to
excavation of the bench and construction
of the invert
- Execution of the internal lining of the
double-layered structure

## Slide 5
Ул.Сребърна
Бул.Т.Каблешков
MS 12-2 /Vitosha/ - commissioned on 20.07.2016
location in the urban layout, construction and view

## Slide 6: 2. Project of the construction of Line 3 - Stage 1 and 2 /2016-2019/
Approved route of Line 3 - 2012: “Vl. Vazov blvd. – Orlov Most - NDK – Krasno Selo – Ovcha
Kupel RD”: Length - 16 km with 16 stations and expected passenger flow of 170 thousand passengers/day;
Completed works related to preparation of the project of Line 3 - 2011-2014:
- Developed route options. Technical-economic justification. Public discussions conducted - 14,15,16.10.2011 and 26.09.
Route approved by the expert counc СО
- Preliminary design - 2010 - 2013; Tender documentations; EIA documentation, EIA decision. Amend. of
GMP and detailed master plans - 2012 – 2015
Preparation of the project of Line 3 for financing under OPTTI 2014-20 – Cost-Benefit Analysis and
Application form – Stage 1 - 2015 /Approved by the EC/, Stage 2 –CBA and AP submitted to the MA –
10.2016:
Phases of construction during the period 2016-2020 included in the OPTTI: Stage 1 and Stage 2
Stage 1: “Vladimir Vazov blvd. – Orlov Most – NDK – Krasno Selo”
- Length: 8 km and 8 metro stations
- Depot and 20 trains
- Start of construction – January 2016 /MS 5 and depot – end of 2016/
- Construction duration - 2016-2019
Stage ІІ: “Krasno Selo RD - Ovcha Kupel RD – Sofia-Pernik rail line”
- Length: 4 km and 4 metro stations and railway stop at MS18.
- Start of construction – phased , starting in the beginning of 2017
- Construction duration 2017-2019
Financing of Stage 1 and Stage ІІ: - OPTTI - EUR 391 mln.
- local – EUR 102 mln.

## Slide 7
Location in the urban layout and construction of MS 6 /near the Off-The-Channel theatre/

## Slide 8: Location of MS ”Orlov Most” in the urban layout /connection to Line 1/
Схема
Phases of construction of MS Orlov Most
Connection Line 1 and Line 3

## Slide 9
Location in the urban layout, structure scheme and construction of MS “Patriarh Evtimiy“
Construction of MS Patriarh Evtimiy

## Slide 10
Layout, section and construction of MS “NDK 2“ from Line 3 (with connection to Line 2)

## Slide 11
MS Medical Academy
location, technological scheme of its construction under “Top down” method
and construction process

## Slide 12
Location in the urban layout
and construction
of MS Bulgaria Boulevard

## Slide 13: Location and construction process of MS “Krasno Selo” at the intersection of Tsar Boris III blvd. and Zhitnitsa str.
Longitudinal section along the axis
of the station

## Slide 14: Layout, longitudinal section and cross section of the tunnels at the central city part of the route of Line 3

## Slide 15
General view of the tunnel boring machine with a diameter of 9.4 m for construction of the double-road tunnels of Line 3 in the city center /accepting at the plant at Germany 10.2015/
Scheme of the tunnel structure and general view of the workshop for production of reinforced concrete segments of the tunnel structure

## Slide 16
General view of the construction
of the launch for the operation
of the tunnel boring machine

## Slide 17
Rolling stock of the Inspiro model produced by the Siemens company
and the 1.5 m high automatically opened barriers for the platforms of Line 3
Станция 1
Станция N
Контролен център
Двоен оптичен ринг
Scheme of the dispatch traffic control Scheme of transport automation

## Slide 18
Sections and sites / Year | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 
Trimester | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Stage І |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1. Central section “MS 6 Zaimov Park – Centre – MS 14 Zhitnitsa str.” with length of 7.150 km and 7 metro stations - Tender and other procedures - Tunnel construction – 42 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2. Section from “MS 5 V. Vazov blvd. - MS 6 Zaimov Park” 650 m long and 1 metro station - Tender and other procedures - Construction – 32 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Supply of rolling stock with transport automation and traffic control (СВТС system) - Tender procedures - Production – 36 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Depot - Tender procedures - Construction – 22 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5. Complex and commissioning tests and putting into operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6. Stage II – section “MS 14 Zhithitsa str. – MS 18 Ring Road” 4.3 km long with 4 metro stations - Tender procedures - Construction – 30 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- Tender and other procedures
- Implementation
Construction schedule of Stage 1 and Stage 2 of Line 3
of Sofia Metro Project

## Slide 22
STAGE І - CONSTRUCTION INSTALATION WORKS | 16.42%
LOT 1 | 15.09%
LOT 2 | 29.28%
LOT 3 | 14.16%
LOT 4 | 18.21%
ENGINEER CONSULTANT – LOT 1, 2, 3 AND 4 | 19.15%
METRO STATION 5 (New contract starting on 01.12.2016) | 0.00%
DEPOT (New contract starting on 01.12.2016) | 0.00%
ENGINEER CONSULTANT - MS 5, DEPOT AND CONTROL SYSTEMS (New contract starting on 10.11.2016) | 0.00%
SUPPLY OF TRAINS AND CONTROL SYSTEMS | 10.00%
SUPPLY OF TRAINS | 10.00%
CONTROL SYSTEMS | 10.00%
STAGE І - CIW + SUPPLY OF ROLLING STOCK | 14.12%
PHISICAL IMPLEMENTATION (OCTOBER 2016)

## Slide 23
Types of costs | Financial plan | Costs paid by the beneficiary | Costs verified by MA | Costs to be verified by MA | Financial rate | 
TOTAL: | 398,178 | 94,8 | 65,229 | 29,576 | 23,82% | 
FINANCIAL IMPLEMENTATION – STAGE 1
/mln. euro/

## Slide 24: Main parameters and public benefits by the Sofia Metro Extension Projects, included in the OPTTI 2014-2020
Total length of the extension:
of Line 2 – 1.3 km with 1 metro station
of Stage 1 and Stage 2 of Line 3 – 12 km with 12 metro stations
Main public benefits from the projects planned to be realized duding the programming period of OPTTI - 2014-2020:
Prognosticated number of passengers from section MS 2-11- МS 2-12 – 20 th. pass./day
Prognosticated number of passengers from Stage 1 and Stage 2 of Line 3 – 130 th. pass./day
- Total number carried passengers by metro after the completion
of the section of Line 2 and Stages 1,2 of Line 3 in 2019 – over 500 th. pass./day
- Additional saved time of traveling in the MPT only from Stages 1 and 2 of L3 – 45 th. hrs daily
- Traffic reduction from Stages 1 and 2 of L3 – over 20-25% along the route of the line
- Reduction of greenhouse gasses /only from Stages 1 and 2 of L3/ – 34 th. tones annually
- Total share of the metro in the public transport system after the completion
of the projects in OPTTI 2014-2020 – section MS 11-МS12 of L2 and Stages 1 and 2 of L 3 - over 45%

## Slide 25: Metropoliten JSC 28-29 November 2016 Prof. PhD, eng. Stoyan Bratoev PhD, eng. Angel Dzhorgov