## Slide 1: “Lessons Learnt” workshop on 18th June 2015, Sofia
Project Implementation Support Service Agreement (PISSA) TA2013040 BG BSF
S1 – Procurement & FIDIC
Dr. Károly Léderer, EIB Claim Expert, Sofia

## Slide 2: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
General thoughts on contract
Legal environment around the PSP Contract
Private contract / Public Contract
(FIDIC) (Procurement)
Some examples on practical issues
Suggested improvements in future NRIC’S contracts
PROCUREMENT & FIDIC

## Slide 3: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
A CONTRACT is
an agreement by which one person bind himself toward an other to transfer, to do or not do something (French Civil Code)
necessary between the parties in order to create an obligation by legal transaction and to alter the contents of an obligation (German Civil Code)
a bilateral arrangement under which each party owed obligations to the other, resting on „bona fides” and included in a consensual contract (Roman concept BC)
THE PHILOSOPHY BEHIND THE CONTRACT
contractual obligations are voluntarily undertaken
to ensure that each party receives the benefits promised by the other party (alternatively their monetary equivalent)
the contract provisions should determine what and against whom they can recover (to secure certainty)
the contract establishes the mandatory mechanism to accomodate to the dynamics of the events
GENERAL THOUGHTS ON CONTRACT
(some very basic principles of both private and public contract)

## Slide 4: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Need contract amendment in case of variations and EoT
FIDIC General Conditions of Contract
Spatial Development Act
Civil Law
Public Procurement Act
Civil Procedure
Code
Duties and responsibilities of the owner, designer, contractor, engineer, incl. separate sets of acts and protocols
General responsibilities of the parties of contract , incl. limitations of liability
LEGAL ENVIRONMENT AROUND THE CONTRACT
DAB role

## Slide 5: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
PRIVATE CONTRACT / PUBLIC CONTRACT
(FIDIC) (PROCUREMENT)
Major Fundamental Principles of and potential conflicts between
Legal and cultural traditions + status of economic and institutional development are important factors also!
Private Law |  | Public Law
FIDIC form of Contract |  | Law of Public Procurement
Equilibrium |  | Asymmetry, unequality
Fairness Reasonability Good Faith Confidence |  | Transparency Accountability
Cost effective |  | Bureaucratic

## Slide 6: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Time bar close in FIDIC (20.1)
Bulgarian civil law (no time bar or in liability cases are very long)
Enforceability of DAB decision in FIDIC (20.7; 14.3 (f))
Bulgarian civil law (court and arbitration decisions)
On site records in FIDIC (no specification)
Bulgarian construction law
FIDIC prevent „time at large” (8.4)
Bulgarian Public Procurement Act – EoT caused by Employer
SOME EXAMPLES ON PRACTICAL ISSUES

## Slide 7: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Better alignment between FIDIC and Bulgarian law procedures, for instance:
  Taking over certificate = Act 15 and ≠ Act 16 => the completion of the works will remain in Contractor's control and will not depend on third’s parties cooperation.
  Defect notification period ≠ General Warrantee period => reasonable time for issuing of Performance Certificate and release of the performance security and retention money, etc.
Clarification of certain amendments to classical FIDIC, for instance:
  Clarifying the limitation of Engineer's powers under Sub-clause 3.1, e.g. shall the Engineer seek Employer’s approval in case of decision under 20.1 or only in case of certifying amounts?
  Are contingencies equated to provisional sums?
  Is the contingencies procedure part of the variation procedure or a separate one?
  Who can sign the trilateral protocol for awarding contingencies – the legal representatives of the parties or their representatives under the contract?
Introduction of flexible options for the Employer to alleviate the restrictions for contract amendments set out n PPA.
SUGGESTED IMPROVEMENTS IN FUTURE NRIC’S CONTRACTS

## Slide 8: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Putting back sub-clause 14.8 – Delayed Payment
  as no compensation for late payment is against the Law (both Civil and Public)
  even if EU funding is not eligable for paying interest on late payment
Deleting additional sentence to sub-clause 20.1 first paragraph: „any additional payment, pursuant to the order of disbursement of contingency expenses amounts provided for the Contract” and
Putting back the omitted sentence: „under any Clause of these Conditions or otherwise in connection with the Contract”
  as in present form the above are limitations of the rights in Civil Law of the Contractor in cases both the quantum exceeds the Contract Price and „otherwise” the Contractor consider himself entitled for a recovering
Delaying additional sentence to sub-clause 20.4 third paragraph: „DAB shall attempt to reconcile both parties and respectively terminate the dispute if possible, then…”shall have its decision”,
  as this task is strongly contradicts to the General Conditions of Dispute Adjudication Agreement and to the Procedural Rules annexed and
  it seriously endangers the enforceability of DAB decision due to application of a wrong procedure
SUGGESTED IMPROVEMENTS IN FUTURE NRIC’S CONTRACTS

## Slide 9: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
CONTRACT ADMINISTRATION WITHIN AND BEYOND THE CONTRACT (VARIATIONS, EoT and CLAIMS)
Contingencies
Only to the extent that they are included in the contract price and are part of the tender documents.
Used successfully for many years by public employers.
Annex under Art. 43, para. 2 of the PPA
Limited opportunities for application in NRIC’s case.
Negotiated procedure under Art. 90 of PPA
Very strict preconditions.
General rules of Civil Law on liabilities
Necessary for extension of Time for Completion.
Can lead to significantly more money for the contractor than contingencies.
The Employer is not relieved from his liability even if the contract is not changed;
The Contractor may be granted additional money as compensation for damages or to be relieved from delay damages.