## Slide 1: “Lessons Learnt” workshop on 18th June 2015, Sofia
Project Implementation Support Service Agreement (PISSA) TA2013040 BG BSF
S 4 – Claim Management
Balázs Gróf, EIB Claim Expert, Sofia

## Slide 2: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Comments on Variations and Claims vs Public Procurement Act (PPA)
Variation procedures
Contractor’s Claims
Risk allocation and Contractor's entitlement as per FIDIC / PSP Contracts / PPA
Conclusions, recommendations
VARIATION ORDERS AND CLAIMS

## Slide 3: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
COMMENTS ON VARIATIONS AND CLAIMS vs PPA
Variation orders and Claims – Practically contract modifications
Public Procurement Act, Article 43
(1) The parties to a public procurement contract may not amend the said contract.
(2) An amendment to a public procurement contract shall be effected by a supplementary agreement to the contract and shall be admissible on an exceptional basis:
1. …where, for reasons brought about through unforeseen circumstances:
(a) the time limits of the contract cannot be complied with, or
(b) …have to be partially replaced, where this is in the interest of the contracting authority and does not lead to an increase of the value of the contract, or
(c) …
Supplementary Provisions 14b. "Unforeseen circumstances" shall be circumstances which have occurred after the conclusion of the contract and do not result from any action or omission of the parties, which could not have been foreseen upon the exercise of due care and render impossible compliance with the terms agreed.
FIDIC Yellow Book: point 1.1.6.8 “Unforeseeable” means not reasonably foreseeable by an experienced contractor…

## Slide 4: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Variation procedure as per Clause 13 is considerably limited
Sub-Clause 13.1 – Material (essential) variations
(a) Technical nature
(i) Technical content with effect on the EU grant agreement
(ii) Technical content against Tender condition
(b) Financial
modifies the Accepted Contract Amount (Приета договорна сума)
Required documents
Variation order
Tri-partite protocol
Supplementary Agreement
and their various combinations depending on the particular Variation
VARIATION PROCEDURES

## Slide 5: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
VARIATION PROCEDURES
Variation which modifies |  | The Accepted Contract Amount: Essential as per S-C 13.1 (b) Financial variation* | 
 |  | Yes | No
The Technical content: Essential as per S-C 13.1 (a) (i) and (ii) | Yes | VO document+ Tri-partite protocol and Supplementary Agreement | VO document+ Supplementary Agreement
 | No | VO document+ Tri-partite protocol and Supplementary Agreement | Variation procedure as per Clause 13
* Reference to PPA Article 43 in Sub-Clause 14.1

## Slide 6: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Claims procedures, Clause 20
FIDIC: entitlements to Extension of Time for Completion+Additional Payment
Handling of Claims - PPA restrictions, therefore, almost all entitlements for Additional Payments are deleted
In principal contingency cannot be disbursed for Claims
Timebars (notices, submission of particulars, evaluation)
Engineer's determination
Disagreement, Dispute resolution
CONTRACTOR’S CLAIMS

## Slide 7: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
RISK ALLOCATION AND ENTITLEMENT AS PER FIDIC/CONTRACT/PPA
Sub-Clause | Heading | Ground | Risk allocation |  | Extension of Time (EoT) |  |  | Additional payment (C: Cost, C+: Cost+Profit) |  | 
 |  |  | FIDIC YB | PSP Contract | FIDIC YB | PSP Contract | PPA Art. 43 | YB | PSP Contract | PPA Art. 43
1.9 | Errors in the Employer’s Requirements (which was not previously discoverable) | Error in the Employer’s Requirements, and an experienced contractor exercising due care would not have discovered the error when scrutinising the Employer’s Requirements under Sub-Clause 5.1 | EMPL | EMPL | Y | Y | N | C+ | C+ | N
2.1 | Right of Access to the Site | Failure by the Employer to give right of access to, or possession of, the Site within required time unless and to extent Employer’s failure was caused by any error or delay by the Contractor | EMPL | EMPL | Y | Y | N | C+ | N | N
4.6 | Co-operation | Instruction by the Engineer to allow specified others’ appropriate opportunities to carry out works | EMPL | EMPL | Y /8.4 (a)/ | Y /8.4 (a)/ | Y/N | C+ | C+ | N
4.7 | Setting Out | Execution of work which was necessitated by an error in items of reference and an experienced contractor could not reasonably have discovered such error and avoided this delay and/or Costs | EMPL | CON | Y | N | N | C+ | N | N
4.12 | Unforeseeable Physical Conditions | Encountering Unforeseeable physical conditions | EMPL | EMPL | Y | Y | Y | C | N | N
4.24 | Fossils | Compliance with the Engineer’s instructions following discovery of fossils on the Site | EMPL | EMPL | Y | Y | Y | C | C | N
7.4 | Testing | Compliance with the Engineer’s instructions or as a result of a delay for which the Employer is responsible | EMPL | EMPL | Y | Y | N | C+ | N | N
8.4 (a) | Extension of Time for Completion | Variations | EMPL | EMPL | Y | Y | Y |  |  | 
8.4 (b) | Extension of Time for Completion | Cause of delay giving an entitlement to EoT under GCC/PCC | EMPL | EMPL | Y | Y | Y/N |  |  | 
8.4 (c) | Extension of Time for Completion | Exceptionally adverse climatic conditions | EMPL | CON | Y | N | N |  |  | 
8.4 (d) | Extension of Time for Completion | Unforeseeable shortages in the availability of personnel or Goods caused by epidemic or governmental actions | EMPL | EMPL | Y | Y | Y |  |  | 
8.4 (e) | Extension of Time for Completion | Any delay, impediment or prevention caused by or attributable to the Employer, the Employer’s Personnel, or the Employer’s other contractor on the Site | EMPL | EMPL | Y | Y | N |  |  | 

## Slide 8: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
RISK ALLOCATION AND ENTITLEMENT AS PER FIDIC/CONTRACT/PPA
Sub-Clause | Heading | Ground | Risk allocation |  | Extension of Time (EoT) |  |  | Additional payment (C: Cost, C+:Cost+Profit) |  | 
 |  |  | FIDIC YB | PSP Contract | FIDIC YB | PSP Contract | PPA Art. 43 | YB | PSP Contract | PPA Art. 43
8.5 | Delays Caused by Authorities | Unforeseeable delay or disruption to the Contractor’s work by authorities | EMPL | EMPL | Y | Y | Y |  |  | 
8.9 | Consequences of Suspension | Compliance with the Engineer’s instructions to suspend and in resuming the works | EMPL | EMPL | Y | Y | Y/N | C | N | N
9.2 | Delayed Tests | Undue delay by Employer to Tests on Completion | EMPL | EMPL | Y | Y | N | C+ | N | N
10.2 | Taking Over of Parts of the Works | Employer’s taking over and/or using a part of the Works oither than such specified in the Contract or agreed by the Contractor | EMPL | CON |  |  |  | C+ | N | N
10.3 | Interference with Tests on Completion | Delay in carrying out Tests on Completion by a cause for which the Employer is responsible | EMPL | EMPL | Y | Y | N | C+ | N | N
11.8 | Contractor to Search | Instruction to search for cause of defect for which the Contractor is not responsible | EMPL | CON |  |  |  | C+ | N | N
12.2 | Delayed Tests | Employer’s delay in Test after Completion | EMPL | CON |  |  |  | C+ | N | N
12.4 | Failure to Pass Tests after Completion | Delay's due to Employer | EMPL | CON |  |  |  | C+ | N | N
13.3 | Variation Procedure | The Contract Price shall be adjusted as a result of Variations | EMPL | EMPL | Y | Y | Y/N | C+ | C+ | N
13.7 | Adjustments for Changes in Legislation | Changes in Laws, which affect the Contractor in the performance of his obligation under the Contract | EMPL | CON | Y | N | N | C | N | Y
14.8 | Delayed payments | Financing charges shall apply if payment is not effected by the Employer as per Contract | EMPL | CON |  |  |  | C | N | N
16.1 | Contractor’s Entitlement to Suspend Work | Suspension or reduction in rate of work by the Contractor | EMPL | EMPL | Y | Y | N | C+ | N | N
16.4 | Payment on Termination | Losses and damages after terminating the Contract | EMPL | CON |  |  |  | Losses+ Damages | N | N
17.4 | Consequences of Employer’s Risks | Rectification of loss or damage to the Works, Goods or Contractor’s Documents due to ERE | EMPL | EMPL | Y | Y | Y/N | C C+ | N | N
19.4 | Consequences of Force Majeure | Force Majeure preventing the Contractor from performing any of his obligations | EMPL | EMPL | Y | Y | Y | C (in some cases) | N | N

## Slide 9: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Sub-Clause | Heading | Risk allocation |  | Extension of Time (EoT) |  |  | Additional payment (C: Cost, C+: Cost+Profit) |  | 
 |  | FIDIC YB | PSP Contract | FIDIC YB | PSP Contract | PPA Art. 43 | FIDIC YB | PSP Contract | PPA Art. 43
1.9 | Errors in the Employer’s Requirements (which was not previously discoverable) | EMPL | EMPL | Y | Y | N | C+ | C+ | N
2.1 | Right of Access to the Site | EMPL | EMPL | Y | Y | N | C+ | N | N
4.6 | Co-operation | EMPL | EMPL | Y /8.4 (a)/ | Y /8.4 (a)/ | Y/N | C+ | C+ | N
4.7 | Setting Out | EMPL | CON | Y | N | N | C+ | N | N
4.12 | Unforeseeable Physical Conditions | EMPL | EMPL | Y | Y | Y | C | N | N
4.24 | Fossils | EMPL | EMPL | Y | Y | Y | C | C | N
7.4 | Testing | EMPL | EMPL | Y | Y | N | C+ | N | N
8.4 (a) | Extension of Time for Completion | EMPL | EMPL | Y | Y | Y/N |  |  | 
8.4 (b) | Extension of Time for Completion | EMPL | EMPL | Y | Y | Y/N |  |  | 
8.4 (c) | Extension of Time for Completion | EMPL | CON | Y | N | N |  |  | 
8.4 (d) | Extension of Time for Completion | EMPL | EMPL | Y | Y | Y/N |  |  | 
8.4 (e) | Extension of Time for Completion | EMPL | EMPL | Y | Y | N |  |  | 
8.5 | Delays Caused by Authorities | EMPL | EMPL | Y | Y | Y |  |  | 
8.9 | Consequences of Suspension | EMPL | EMPL | Y | Y | Y/N | C | N | N
9.2 | Delayed Tests | EMPL | EMPL | Y | Y | N | C+ | N | N
10.2 | Taking Over of Parts of the Works | EMPL | CON |  |  |  | C+ | N | N
10.3 | Interference with Tests on Completion | EMPL | EMPL | Y | Y | N | C+ | N | N
11.8 | Contractor to Search | EMPL | CON |  |  |  | C+ | N | N
12.2 | Delayed Tests | EMPL | CON |  |  |  | C+ | N | N
12.4 | Failure to Pass Tests after Completion | EMPL | CON |  |  |  | C+ | N | N
13.3 | Variation Procedure | EMPL | EMPL | Y | Y | Y/N | C+ | C+ | N
13.7 | Adjustments for Changes in Legislation | EMPL | CON | Y | N | N | C | N | Y
14.8 | Delayed payments | EMPL | CON |  |  |  | C | N | N
16.1 | Contractor’s Entitlement to Suspend Work | EMPL | EMPL | Y | Y | N | C+ | N | N
16.4 | Payment on Termination | EMPL | CON |  |  |  | Losses+ Damages | N | N
17.4 | Consequences of Employer’s Risks | EMPL | EMPL | Y | Y | Y/N | C/C+ | N | N
19.4 | Consequences of Force Majeure | EMPL | EMPL | Y | Y | Y | C (in some cases) | N | N

## Slide 10: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Further harmonization of FIDIC/Contract Conditions/PPA required
Contract terms shall be used consequently at contract drafting
Procedures must be clear/clarified at the beginning – Manual to be prepared (Memorandum of Understanding)
Adequate Variation orders and Claims register
  Basis, contract reference
  Records
  EoT and Value
  Status
  Regular follow up to define/agree in required (timely) actions and control
Timely involvement of others (e.g. Managing Authority, Financing Authority, RAEA, MRD)
etc.
CONCLUSIONS, RECOMMENDATIONS

## Slide 11: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Variation order document shall include the Engineer’s confirmation on the followings (such information may be required from the Contractor as well):
  whether the modification is essential to achieve the purposes of the project/procurement, and
  is not included in the Contract, and
  the event or circumstance giving rise to the modification does not fall under the Contractor’s risk, and
  cannot be technically and/or economically separated from the Contract, or although separable, are strictly necessary to the performance of the Contract, and
  is unforeseen by the Parties, and
  procedure to be followed shall be defined/advised.
Pricing
  detailed price breakdown required for Variations, unit prices?
CONCLUSIONS, RECOMMENDATIONS