## Slide 1: “Lessons Learnt” workshop on 18th June, Sofia
Project Implementation Support Service Agreement (PISSA) TA2013040 BG BSF
S3: “Assessment, management and pricing of risks (including reliable cost evaluation)”
Goran Crnogorcevic, EIB Cost Engineer & Tamás Kozák, EIB Risk Expert, Sofia

## Slide 2: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Basic Project Cycle Management (PCM) Project development is a continued process and integrated process, , in a “step by step development” consolidating each “step” between the parties involved in the process. The process follows the principles of the PCM with its six phases of project Identification & Programming, Development, Assessment, Financing, Implementation and Evaluation & Audit.
I
Identification of the Idea/Project
Programming
II
Development
III
Assessment
PCM
Project Cycle Management
IV
Financing
V
Implementation
VI
Evaluation and Audit
Macro level
The generic PCM phases
Identification & Programming
Development
Assessment & Project fiche
Financing & Financing agreement
Implementation & Tender dossier
Evaluation & Audit

## Slide 3: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
  FROM IDENTIFICATION & PROGRAMMING TO IMPLEMENTATION
  DEVELOPMENT MODEL
THE SCREENING MODEL & THE PCM
IDENTIFICATION & PROGRAMMING
Long List
Priorities
Project Screening
Selection Criteria
Short List
Project Proposal
INVESTMENT PROJECTS
Model Projects for
Investment, e.g.
Elin Pelin-Septemvri
Volijak-Dragoman
Plovdiv-Burgas Phase 2
Etc.
PCM
PROJECT
IMPLEMENTATION
MODEL
ZUT or
FIDIC or
PRAG, IFIs, EBRD, EIB, WB etc.
The PCM Phases | (I) Identification of Idea/Programming (II) Development (III) Assessment | (IV) Financing (V) Implementation (VI) Evaluation and Audit

## Slide 4: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
PROJECT LIFE : PREPARATION – IMPLEMENTATION - EXPLOATATION
PROJECT REALIZATION
PRE CONSTRUCTION PHASE CONSTRUCTION PHASE
REQUIREMENTS SPECIFICATIONS
- INVESTIGATION WORKS - CONSTRUCTION WORKS
- DESIGNS - DESIGNS

## Slide 5: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Example 1:
9 Pregnant Woman 1 month
CORRECT MODEL
WRONG INPUT
Example 2:
1 Pregnant Woman 9 month
CORRECT MODEL
CORRECT INPUT
Conclusion: There is no wrong models, only wrong inputs
PROPER CONTRACT MODEL GOOD RESULTS
PROPER INPUTS MINIMUM RISKS
BAD RESULTS
MAXIMUM RISK
GOOD RESULTS
MINIMUM RISK

## Slide 6: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Project case 1: Plovdiv –Svilengrad Project, position 2, Harmanly – Svilengrad
CONTRACTOR’S INTERIM COMPENDIUM CLAIM for QUANTUM COST
Daily Rates
a. Additional Overhead BGN 25.502,22
b. Retention of Railway Mechanisation BGN 18.322,45
c. Pre-financing BGN 7.270,14
d. Additional staff for observation BGN 903,53
e. Prolonged engagement of staff for superstructure BGN 3.328,95
f. Additional fees for external consultants BGN 2.892,00
TOTAL COMPENDIUM CLAIM DAY COST BGN 58.219,29
Working position 2 – Design for project BGN 2.031.420,76
DESIGN FOR PROJECT = 35 COMPENDIUM CLAIM DAY COST
Assessed project additional cost cca BGN 40* million ( +33%)
Assessed project additional time for completion 20 month (+67%)
Conclusion:
INVEST IN PREPARATION = GET IN IMPLEMENTATION
SHORT PREPARATION = LONG CONSTRUCTION

## Slide 7: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Project case 2: Rehabilitation of 12 large slopes
on the Vrbnica-Bar railway line
Scenario of possible solutions and average cost
Protection steel mesh…………………………………200-1000 €/m’
Slope stabilization by concrete “torkret”………........ > 1000 €/m’
Retention walls………………………………………....... > 1000 €/m’
Galleries………………………………………………....... > 1000 €/m’
Tunnels……………………………………………...15.000-25.000 €/m’
Proposed mode: FIDIC Yellow Book 1999
Available input: Feasibility Study + Employers Requirements
Conclusion:
High risk of claims, sub clause 4.12 Unforeseeable Physical Conditions.
Unforeseeable adverse sub-surface conditions and lack of sufficient and adequate information about the construction site in the tender phase. One of the most occasional claims source.
PROJECT TARGET: to be in time, within the budget, certain quality

## Slide 8: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
The most applied FIDIC contract model is FIDIC Red Book all issues
FIDIC Red Book > ∑ FIDIC models issues
Region statistic of application: Red Book vs Yellow Book = 30:70
Yellow Book becomes alamode in infrastructure!
Not selective application = additional costs and time for completion
Main causes:
1. Long lasting and non comprehensive land acquisition process;
2. Short period for preparation;
3. Deficiency of investigation works;
4. Deficiency in scope of design works and technical requirements;
5. Lack of Stakeholders responsibility for their requirements.

## Slide 9: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
III.ii.2 Schedule of Prices |  | 
III.ii.2.X | Main works item | 
Item | Description | Amount (Currency)
X.X.1 | Item description | 
X.X.2 | Item description | 
III.ii.2.X Provisional Sums |  |  |  | 
Item | Description | Unit | Quantity | 
X.X.1 | PROVISIONAL SUM |  |  | Contractor’s % Clause 13.5
X.X.1.1 | Description |  | XXX.XXX | 
X.X.1.2 | Description |  | XXX.XXX | 
Etc.
Etc.

## Slide 10: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Item | Description | Unit | Qty | Rate | Amount (currency)
X.X.2 | Day work to track work completion and track rehabilitation works |  |  |  | 
X.X.X.1 | Labour |  |  |  | 
X.X.X.1.1 | Engineer | h | 500 |  | 
X.X.X.1.2 | Technician | h | 800 |  | 
X.X.X.1.3 | Foreman | h | 1000 |  | 
X.X.X.1.4 | Surveyor | h | 500 |  | 
X.X.X.1.5 | Skilled Labourer | h | 3000 |  | 
X.X.X.1.6 | Steel Worker (welder, fitter etc) | h | 1000 |  | 
X.X.X.1.7 | Unskilled Labourer | h | 3000 |  | 
X.X.X.1.8 | Machin operator | h | 500 |  | 
X.X.X.1.9 | Driver | h | 500 |  | 
X.X.X.1.10 | Xxxx |  |  |  | 
X.X.X.1.11 | Yyxx |  |  |  | 
 | Total of Works carried to summary |  |  |  | 

## Slide 11: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Item | Description | Unit | Qty | Rate | Amount (currency)
X.X.2 | Day work to track work completion and track rehabilitation works |  |  |  | 
X.X.X.2 | Equipment (incl. crew) |  | … |  | 
X.X.X.2.1 | Two way excavator | h | 700 |  | 
X.X.X.2.2 | Portal crane | h | 500 |  | 
X.X.X.2.3 | Tamping machine | h | 200 |  | 
X.X.X.2.4 | Profilator | h | 100 |  | 
X.X.X.2.5 | Trolley | h | 100 |  | 
X.X.X.2.6 | 2 axle wagons | h | 200 |  | 
X.X.X.2.7 | Power Wrench | h | 200 |  | 
X.X.X.2.8 | Rail cutter | h | 500 |  | 
X.X.X.2.9 | Rail driller | h | 500 |  | 
X.X.X.2.10 | Sleeper driller | h | 500 |  | 
X.X.X.2.11 | Rail Mover | h | 200 |  | 
X.X.X.2.12 | Ballast wagons | h | 200 |  | 
 | Total of Works carried to summary |  |  |  | 

## Slide 12: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Item | Description | Unit | Qty. | Rate | Amount (Currency)
X.X.2 | Day work to track work completion and track rehabilitation works |  |  |  | 
X.X.X.3 | Material (incl. transport to Site) |  | … |  | 
X.X.X.3.1 | Material for embankment | m3 | 1000 |  | 
X.X.X.3.2 | Ballast for superstructure | m3 | 500 |  | 
X.X.X.3.3 | Pre stressed concrete sleepers | piece | 162 |  | 
X.X.X.3.4 | Turnouts 60E1-300-1:9 | piece | 1 |  | 
X.X.X.3.5 | Turnouts 49E1-300-1:9 | piece | 1 |  | 
X.X.X.3.6 | Rail type 60E1 | t | 100 |  | 
X.X.X.3.7 | Concrete C30 | m3 | 100 |  | 
X.X.X.3.8 | Reinforcement Steel | t | 10 |  | 
X.X.X.3.9 | Catenary poles | piece | 100 |  | 
X.X.X.3.10 | Yyyyy |  |  |  | 
X.X.X.3.11 | Zzzzz |  |  |  | 
 | Total of Works carried to summary |  |  |  | 

## Slide 13: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Schedule No. | Description | Amount (Currency)
III.ii.2.1 | Works description | 
III.ii.2.2 | Works description | 
ETC. |  | 
III.ii.2.8 | Works description | 
 | Item | 
 | Item | 
 | Item | 
III.ii.2.9 | Provisional Sums and Daywork | 
 | Provisional Items | 
 | Dayworks | 
Subtotal items III.ii.2.1 to 2.9 exclusive of VAT |  | 
Contingence Sum 2-3 % of Subtotal |  | 
Subtotal exclusive of VAT |  | 
VAT applicable in Bulgaria at the rate of 20% |  | 
GRAND TOTAL |  | 
III.ii.3 Grand Summary
The Tenderer has to follow the structure as below for the Grand Summary sheet

## Slide 14: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
TRACK RECORD TO RISK REGISTER
Phase 4.1 Dimitrovgrad – Harmanly;
Phase 4.2 Harmanly - Svilengrad

## Slide 15: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Design
Project Section | Threat | Blocking Cause | Risk
Phase 4.2 Harmanli - Svilengrad, Section 4 | Lack of proper assessment of land proprietary - ENVIRONMENT | Maritsa river bed deepening | Weather pulls back the additional ground work
Phase 4.2 Harmanli - Svilengrad, Section 5 | Additional investment expectation by local government - exercise of STAKEHOLDER power | Change in design in pedestrian underpass in Harmanli | Delay in Permission

## Slide 16: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Construction
Project Section | Threat | Blocking Cause | Risk
Phase 4.2 Harmanli - Svilengrad, Section 3, Ljubimets | Bureucracy in the land aquisition processes - LEGAL | There is not construction permit (in progress ) | May cause delay in the constructor input for civil work
Phase 4.2 Harmanli - Svilengrad, Section 4 | Due to heavy rains - ENVIRONMENT | Harmanli rive diversion build flood protection | Weather pulls back the additional ground work
Svilengrad border | STAKEHOLDER requirement | Additional Schengen fence in Harmanli requested by the Custom | Constrain within the budget
Phase 4.1 Harmanli - Dimitrovgrad, Section 3.3, km 254+800 - 258 350. | NATURA 2020 Directives - LEAGAL | Considerable work remains to conclude the bridge decks, piers and waterproofing. | Significant risk in completion,

## Slide 17: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Post - Construction
Project Section | Threat | Blocking Cause | Risk
General | Uncertainty in the employer's long approval processes - LEGAL | Disputing in take-over process on ACT15 or ACT16. | Sub sections could not be placed for Act 15 procedure

## Slide 18: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
Training
Approaching the Risk:
Mitigate risk
Avoid risk to the degree possible
Concept of “Acceptable Risk”
Risk Management Targets
Cost
Time
Quality

## Slide 19: Project Implementation Support Service Agreement – Activity 3, “Lessons Learnt” workshop
THANK YOU FOR KIND ATTENTION
БЛАГОДАРИМ ВИ ЗА ВАШАТА ВНИМАНИЕТО